Summer Pilot Plan

Math + Making Studio

Pilot location: 24th & Douglass, Noe Valley, San Francisco

Free space · Summer only

# 1. What this pilot is actually for

This is not “a fun summer.” It is a cheap experiment designed to answer the three questions that determine whether the larger business is real — before anyone signs a Peninsula lease or buys a single power tool.

The three questions:

- Does the pedagogy work? When Jack teaches math through making, do kids genuinely engage, and do parents perceive real learning? This is the core thesis and it is location-independent.

- Will people pay, return, and refer? Can we fill seats at a real price, get families to come back, and generate word of mouth in an affluent, education-intensive neighborhood?

- Can Jack’s instinct become repeatable curriculum? The eventual franchise/PE exit only works if a non-Jack can deliver the experience. This summer is our first test of building “Jack-in-a-box.”

What this pilot deliberately does NOT test (and that’s fine — we test the cheap, fundamental questions first):

- The real maker-space build-out, tools, and the premium “wow” experience.

- The Peninsula market specifically (this is SF / Noe Valley).

- The capital-intensive unit economics the scale story ultimately depends on.

The materials constraint (cardstock, tape, straws, string) is a feature, not a bug. Paper is a mathematically rich making medium, and a near-zero materials budget means almost all our learning is free.

# 2. Success criteria — decide this NOW, before we start

If we don’t define “pass” up front, we’ll finish August with a warm feeling and no decision. These are the go/no-go targets for committing to a paid Peninsula location.

| Dimension | Metric | Target to “pass” |
| --- | --- | --- |
| Demand | Fill rate across camp weeks (enrolled ÷ capacity) | ≥ 75% |
| Pricing | Price point achieved without discounting | ≥ $475 / week |
| Engagement | Parent rating (simple 1–5 end-of-week survey) | ≥ 4.5 avg |
| Retention / referral | Families who rebook OR join the fall waitlist OR refer | ≥ 50% |
| Systematization | Documented, repeatable lesson modules by end of summer | ≥ 15 modules |
| Deliverability test | A non-Jack (Gail) successfully runs ≥ 1 session from Jack’s written plan | Pass / fail |

If we hit demand + engagement + retention but fail systematization, the business is a great lifestyle business but not yet a scalable asset — which is exactly the tension worth knowing about early.

# 3. Program structure

Jack is solo this summer, so the design has to be runnable by one person while still testing everything. The structure below concentrates his teaching time and protects time for the lesson-documentation work that the scale thesis depends on.

Two products:

## (A) Weekday morning camps — the demand + intensive-engagement engine

- Monday–Friday, 9:00 am–12:00 pm (3 hrs/day, 15 hrs/week)

- One cohort at a time, cap 8 kids (matches the small-group premium and common 1:8 industry ratios)

- Alternate age bands week to week: Elementary (ages ~7–10) and Middle (ages ~11–13)

- Each week is a self-contained theme so families can buy one or several weeks

## (B) Saturday “Open Studio” family workshops — the funnel + referral engine

- 90-minute drop-in sessions, ~$45–$60 per child, parents welcome and involved

- Low commitment, easy to try, designed to convert into camp enrollments and generate word of mouth

- Doubles as Ann’s content-capture day (with photo releases on file)

Why this shape: camps generate real revenue and concentrate Jack’s hours; Saturdays are cheap top-of-funnel that directly test referral and conversion. Afternoons stay free for prep, parent conversations, and writing up lesson modules.

# 4. Curriculum arc (cardstock / tape / straws / string)

Each module follows the same template — this template is the systematization work:

Build goal (what they make) → Math revealed (the concept hiding inside it) → Discovery question (what Jack asks to make them find it) → Takeaway (the object they bring home)

The takeaway object matters: it’s what the parent sees on the kitchen table, and it’s free marketing.

## Elementary themes (ages ~7–10)

- Shapes that Build Themselves — fold Platonic solids from nets; count faces, edges, vertices; discover Euler’s formula (V − E + F = 2) by noticing the pattern.

- Tiles That Never Leave a Gap — design tessellating tiles; explore symmetry, flips, and slides; Escher-style art.

- Drawing Curves with Straight Lines — curve-stitching / string art on cardstock; a parabola appears from nothing but straight threads.

- What Makes Things Strong? — build a cardstock bridge that holds weight; discover why triangles win.

- The Math of Snowflakes — fold-and-cut symmetry; predict the number of points before unfolding.

## Middle themes (ages ~11–13)

- Modular Origami & the Hidden Solids — assemble Archimedean solids; truncation, duals, and why only certain shapes work.

- Saddles from Straight Straws — build a hyperbolic-paraboloid (hypar) from straws and string; straight pieces, curved surface.

- Hexaflexagons — fold a paper strip into a shape with hidden faces; cycles, combinatorics, and a genuine “wait, what?” moment.

- One-Sided Paper — Möbius strips; predict what happens when you cut one in half, then again; an intro to topology.

- Building Infinity — a collaborative Sierpinski tetrahedron from many small units; self-similarity, scaling, and fractional dimension.

A camp week = one theme, ~3–5 modules deep, ending Friday with a small showcase parents are invited to (engagement signal + referral moment + content for Ann).

# 5. Pricing & enrollment targets

Current SF/Peninsula 2026 comps (mostly full-day, ~6 hrs): specialty STEM camps run roughly $500–$750/week, single-day drop-ins ~$110–$149, common 1:8 ratios, and frequent ~$79 annual registration fees. Most comps are coding/robotics/LEGO — your PhD-led, tiny-group, math-through-making angle is genuinely differentiated and can sit at the premium end per hour even at a half-day length.

Recommended test pricing:

- Camp week (half-day, cap 8): anchor at $525/week. Accessible on a per-week basis versus full-day comps, but a premium per-hour rate justified by a PhD instructor and an 8-kid cap. Hold the line — discounting muddies the demand signal.

- Optional stretch test: run one week at $625 (“Math PhD Master Studio”) to probe the ceiling.

- Saturday Open Studio: $45–$60 drop-in.

- Sibling / multi-week: small multi-week discount (e.g., 5%) is fine; avoid deep discounts.

Enrollment math (illustrative):

- 6 camp weeks × 8 seats = 48 seat-weeks of capacity.

- At 75% fill and $525 → ~36 enrollments → ~$18,900 gross for the summer.

- This number is not the point — it’s a signal. The questions it answers: did they enroll, at this price, without begging? Did they come back?

# 6. Roles & responsibilities

Jack — Chief Maker / the product. Designs and delivers every session. Critically: writes up each module in the template format as he goes. The curriculum artifact is a deliverable, not a nicety — it’s the thing a buyer eventually pays for.

Ann — Marketing & enrollment. Owns the “fill the seats” number. Build a simple landing/registration page, run Instagram, work the Noe Valley parent channels (neighborhood Facebook groups, local elementary/middle school parent lists, the 24th Street corridor, library and café flyers). Owns the referral mechanic and captures content on Saturdays. Tracks cost-per-enrollment.

Gail — Operations, legal & the deliverability test. Waivers and liability releases, registration/payment system, intake forms (allergies, emergency contacts, photo release), refund policy, and appropriate summer insurance — minors plus scissors and supervision is still a liability surface even without power tools. As a credentialed teacher, Gail is also the ideal person to run one session from Jack’s written plan — our direct test of whether the curriculum travels beyond Jack.

You — GM / experiment owner. Own the budget, the metrics dashboard, the weekly review, and the go/no-go call. Your job is to keep this a measured experiment and protect Jack’s documentation time from being eaten by operations.

# 7. Setup, materials & logistics

Space prep: worktables and chairs, material storage bins, a “gallery wall” to display builds (great for kids, parents, and Ann’s photos), sign-in/out sheet, posted schedule.

Materials kit (near-zero cost): assorted cardstock (weights/colors), masking/painter’s tape, child-safe scissors, rulers, straws, string/yarn, hole punches, glue sticks, compasses/protractors, and printed nets/templates. Budget ~$300–$500 for the whole summer.

Safety / supervision: clear adult-to-child ratio, sign-in/out procedure, allergy and emergency info on file, basic first-aid kit, and a plan for a second adult present (helps with both safety and the deliverability test).

# 8. Measurement plan

Keep one simple shared sheet. Track weekly:

- Funnel: inquiries → registrations → paid → attended. Plus Ann’s spend ÷ enrollments = cost-per-enrollment.

- Engagement: daily attendance, modules completed, end-of-week parent rating (1–5), one open-text “what would you change?”

- Retention / referral: rebookings, fall-waitlist sign-ups, referrals generated.

- Systematization: running count of documented modules; notes on what needed Jack vs. what Gail could run cold.

- Economics signal: revenue per week, Jack’s hours, implied $/hour, materials spend.

Hold a 30-minute Friday review every week. Adjust the next week’s marketing and format based on what the numbers say — that responsiveness is itself part of the experiment.

# 9. Timeline

| Phase | Weeks | Focus |
| --- | --- | --- |
| Setup & soft launch | Weeks 1–2 | Space prep, registration page live, Ann’s marketing push, first Saturday Open Studio as a “soft open” |
| Camps run | Weeks 3–8 | 6 camp weeks (alternating age bands) + weekly Saturday studios; Jack documents modules; Gail runs her test session |
| Wrap & decide | Week 9 | Compile metrics against Section 2 targets; written go/no-go on a paid Peninsula location |

# 10. The decision this buys

If the pilot passes Section 2, you’ve cheaply de-risked the two things that matter most — the teaching works and people will pay — and you’ve started building the curriculum asset the exit depends on. That justifies signing a real Peninsula maker space and testing the capital-intensive half of the model.

If it passes on demand/engagement but fails on systematization, you’ve learned something just as valuable: this is a wonderful founder-run studio but not yet a franchisable asset, and the next year’s work is turning Jack into curriculum before you scale.

Either way, you’ll have replaced opinion with evidence — for the price of cardstock and a free room in Noe Valley.